## Executive Summary
NoteSnap — Product Launch Budget & Cash Flow Model
Prepared for: | Executive Management
Date: | March 2026
Product: | NoteSnap — AI-Powered Learning Platform
Market: | Global (English + Hebrew)
Timeline: | 4-8 weeks to launch
Monthly Cost Summary by User Scale (Mixed Activity)
| 50 Users | 100 Users | 500 Users | 1,000 Users | 5,000 Users
Claude AI API (avg mix) | 665 | 1330 | 6650 | 13300 | 66500
Supabase (DB/Auth/Storage) | 0 | 0 | 25 | 25 | 599
Vercel Hosting (Pro) | 20 | 20 | 20 | 20 | 20
Recraft API (Diagrams) | 12 | 24 | 120 | 240 | 1200
E2B Sandbox (Compute) | 5 | 10 | 50 | 100 | 500
Resend (Email) | 0 | 0 | 20 | 20 | 20
Domain + SSL | 1.25 | 1.25 | 1.25 | 1.25 | 1.25
Marketing & Growth/month | 500 | 1000 | 3000 | 5000 | 15000
Contractors & Professionals/month | 2000 | 2000 | 3000 | 5000 | 10000
TOTAL Monthly Cost
Revenue Scenarios (Monthly) — see Pricing Models sheet for detail
Pricing Model | 50 Users | 100 Users | 500 Users | 1,000 Users | 5,000 Users
A: Freemium ($0 / $9.99 / $19.99) | 100 | 300 | 2500 | 6000 | 35000
B: Subscription ($9.99 / $19.99) | 250 | 600 | 4000 | 9000 | 50000
C: Pay-per-Use (credits) | 150 | 400 | 3000 | 7000 | 40000
D: Free (no revenue) | 0 | 0 | 0 | 0 | 0
Net Monthly Profit/(Loss) by Model
A: Freemium ($0 / $9.99 / $19.99)
B: Subscription ($9.99 / $19.99)
C: Pay-per-Use (credits)
D: Free (no revenue)
Key Insight
Break-even requires ~200-300 paying users on Subscription model (B).
Free model (D) is viable for up to ~100 users with total monthly cost under $3.5K.

## AI Cost Breakdown
Claude API Cost Model — Per-Action Breakdown
Anthropic Claude Sonnet 4.6 Pricing
Input tokens (per 1M) | 3
Output tokens (per 1M) | 15
Cost Per User Action
Action | Input Tokens | Output Tokens | Input Cost | Output Cost | Total Cost/Action | Source
Course Generation (upload→course) | 8000 | 16000 |  |  |  | Anthropic API
Lesson Expansion | 4000 | 8000 |  |  |  | Anthropic API
Homework Check | 3000 | 4000 |  |  |  | Anthropic API
Chat Message | 2000 | 2000 |  |  |  | Anthropic API
Practice Question Batch | 3000 | 4000 |  |  |  | Anthropic API
Exam Generation | 4000 | 8000 |  |  |  | Anthropic API
Walkthrough Step | 3000 | 4000 |  |  |  | Anthropic API
Diagram Schema (Claude) | 2000 | 3000 |  |  |  | Anthropic API
Search Query | 1500 | 2000 |  |  |  | Anthropic API
Help Request | 2000 | 3000 |  |  |  | Anthropic API
Prepare Guide Gen | 5000 | 12000 |  |  |  | Anthropic API
Cheatsheet Generation | 3000 | 6000 |  |  |  | Anthropic API
User Activity Profiles (Actions per User per Month)
Action | Light User | Medium User | Heavy User
Course Generation | 2 | 5 | 12
Lesson Expansion | 5 | 15 | 40
Homework Check | 10 | 30 | 80
Chat Message | 20 | 60 | 150
Practice Question Batch | 5 | 15 | 40
Exam Generation | 1 | 3 | 8
Walkthrough Step | 5 | 15 | 40
Diagram Generation | 3 | 10 | 25
Search Query | 5 | 15 | 30
Help Request | 2 | 5 | 10
Prepare Guide Gen | 1 | 3 | 6
Cheatsheet Generation | 1 | 2 | 5
Monthly AI Cost Per User Profile
Action | Light $/mo | Medium $/mo | Heavy $/mo
Course Generation
Lesson Expansion
Homework Check
Chat Message
Practice Question Batch
Exam Generation
Walkthrough Step
Diagram Generation
Search Query
Help Request
Prepare Guide Gen
Cheatsheet Generation
TOTAL AI Cost/User/Month
Total Monthly AI Cost by User Scale (Assuming 40% Light / 40% Medium / 20% Heavy)
User Count | Light Users | Medium Users | Heavy Users | Total AI Cost/Month | Avg Cost/User
50
100
500
1000
5000

## Infrastructure Costs
Infrastructure & Service Costs — Monthly Breakdown
Service Cost by User Scale
Service | 50 Users | 100 Users | 500 Users | 1,000 Users | 5,000 Users | Notes
Supabase | 0 | 0 | 25 | 25 | 599 | Free→Pro ($25) at 500MB. Team ($599) at 5K users
Vercel Pro | 20 | 20 | 20 | 20 | 20 | Pro plan $20/mo. Enterprise if >100K visitors
Recraft API | 12 | 24 | 120 | 240 | 1200 | ~$0.04/image. 3-25 diagrams/user/mo avg
E2B Sandbox | 5 | 10 | 50 | 100 | 500 | $0.16/hr. ~30sec avg per execution
Resend Email | 0 | 0 | 20 | 20 | 20 | Free up to 100/day. Pro $20/mo
Domain (notesnap.app) | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | $15/year = $1.25/mo
Monitoring (Sentry/LogRocket) | 0 | 0 | 26 | 26 | 89 | Free→Dev ($26)→Team ($89)
CDN / Image Optimization | 0 | 0 | 0 | 20 | 50 | Vercel Image Opt included in Pro
Analytics (Mixpanel/PostHog) | 0 | 0 | 0 | 0 | 450 | Free tier sufficient <1K users
Backup & Disaster Recovery | 0 | 0 | 10 | 25 | 50 | DB snapshots, offsite backup
TOTAL Infrastructure/Month
One-Time Setup Costs
Item | Cost |  |  |  |  | Notes
Landing Page Design & Copy | 1500 |  |  |  |  | Professional copywriter + designer
SEO Audit & Optimization | 800 |  |  |  |  | Technical SEO + content optimization
Legal (Privacy Policy, ToS, GDPR) | 2000 |  |  |  |  | Lawyer review for global compliance
Logo & Brand Assets Refresh | 500 |  |  |  |  | Polish existing brand for launch
App Store / PWA Setup | 300 |  |  |  |  | If going PWA route
Payment Integration (Stripe) | 500 |  |  |  |  | Setup, testing, webhook config
Onboarding Flow Design | 800 |  |  |  |  | UX design + implementation
QA & Load Testing | 600 |  |  |  |  | Pre-launch testing across devices
Security Audit | 1000 |  |  |  |  | Pen test + vulnerability scan
Launch PR & Content Pack | 1200 |  |  |  |  | Press kit, blog posts, social assets
TOTAL One-Time Setup

## Pricing Models
Revenue Projections — Four Pricing Strategies
Model A: Freemium — Free tier + $9.99/mo Basic + $19.99/mo Pro
Assumption: 60% free, 25% Basic ($9.99), 15% Pro ($19.99)
Metric | 50 Users | 100 Users | 500 Users | 1,000 Users | 5,000 Users
Free Users (60%) | 30 | 60 | 300 | 600 | 3000
Basic Users @ $9.99 (25%) | 12 | 25 | 125 | 250 | 1250
Pro Users @ $19.99 (15%) | 8 | 15 | 75 | 150 | 750
Monthly Revenue
Model B: Subscription Only — 14-day free trial, then $9.99/mo or $19.99/mo
Assumption: 50% convert after trial. Of converts: 60% Basic, 40% Pro
Metric | 50 Users | 100 Users | 500 Users | 1,000 Users | 5,000 Users
Trial Users (not paying) | 25 | 50 | 250 | 500 | 2500
Basic Subscribers @ $9.99 (30%) | 15 | 30 | 150 | 300 | 1500
Pro Subscribers @ $19.99 (20%) | 10 | 20 | 100 | 200 | 1000
Monthly Revenue
Model C: Pay-per-Use — Credit packs ($4.99/50cr, $9.99/120cr, $24.99/350cr)
Assumption: Avg spend $3/mo (light), $10/mo (med), $25/mo (heavy). Mix: 40/40/20
Metric | 50 Users | 100 Users | 500 Users | 1,000 Users | 5,000 Users
Light Users ($3/mo avg) — 40% | 60 | 120 | 600 | 1200 | 6000
Medium Users ($10/mo avg) — 40% | 200 | 400 | 2000 | 4000 | 20000
Heavy Users ($25/mo avg) — 20% | 250 | 500 | 2500 | 5000 | 25000
Monthly Revenue
Model D: Free — No Revenue (Growth Phase / Fundraising Strategy)
Focus: User acquisition, engagement metrics, fundraising based on traction
Metric | 50 Users | 100 Users | 500 Users | 1,000 Users | 5,000 Users
Monthly Revenue | 0 | 0 | 0 | 0 | 0
KPI: Monthly Active Users (MAU) | 50 | 100 | 500 | 1000 | 5000
KPI: Avg Sessions/User/Week | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
Fundraising valuation multiplier | $50-150 per MAU in EdTech (seed stage)

## 12-Month Cash Flow
12-Month Cash Flow Projection — Subscription Model (B) @ 500 Users Target
Scenario: Grow from 0 → 500 active users over 12 months
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | TOTAL
USER GROWTH
New Users | 20 | 30 | 40 | 50 | 50 | 50 | 40 | 40 | 40 | 50 | 50 | 40
Churn Rate | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5%
Active Users (cumulative)
Paying Users (50% conversion)
REVENUE
Avg Revenue/Paying User | 13.99 | 13.99 | 13.99 | 13.99 | 13.99 | 13.99 | 13.99 | 13.99 | 13.99 | 13.99 | 13.99 | 13.99
Monthly Revenue
COSTS
Claude AI API
Infrastructure | 38 | 38 | 38 | 60 | 60 | 60 | 90 | 90 | 90 | 120 | 120 | 120
Marketing & Growth | 2000 | 1500 | 1500 | 1500 | 1000 | 1000 | 1000 | 1000 | 1000 | 1500 | 1500 | 1000
Contractors / Professionals | 3000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
One-Time Setup (M1 only) | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL Costs
NET Monthly Cash Flow
Cumulative Cash Position

## Launch Plan
NoteSnap Product Launch Plan — Detailed Timeline
Week | Task | Owner | Cost Est. | Priority | Dependencies
PHASE 1: PRE-LAUNCH (Weeks 1-2)
W1 | Legal: Privacy Policy + ToS + GDPR compliance | Lawyer | $2,000 | P0 | None
W1 | Landing page: hero, features, waitlist, pricing | Designer+Dev | $1,500 | P0 | None
W1 | SEO audit: meta tags, sitemap, structured data | SEO Specialist | $800 | P0 | Landing page
W1 | Payment integration: Stripe setup + webhooks | Developer | $500 | P0 | Pricing decision
W1 | Analytics: Mixpanel/PostHog + conversion funnels | Developer | $0 | P1 | None
W1 | Brand refresh: logo polish, social banners, favicon | Designer | $500 | P1 | None
W2 | Onboarding flow: first-use wizard, sample content | UX+Dev | $800 | P0 | None
W2 | Email sequences: welcome, activation, day-3 nudge | Copywriter | $400 | P0 | Resend setup
W2 | Performance optimization: Lighthouse 90+, Core Web Vitals | Developer | $300 | P1 | None
W2 | Security audit: OWASP scan, pen test, rate limiting | Security | $1,000 | P0 | None
W2 | QA: cross-browser, mobile, RTL, accessibility | QA Tester | $600 | P0 | None
W2 | Social media: create accounts, schedule launch posts | Marketing | $200 | P1 | Brand assets
PHASE 2: SOFT LAUNCH (Weeks 3-4)
W3 | Beta invites: 50 users from waitlist / networks | Founder | $0 | P0 | Phase 1 done
W3 | Feedback loop: in-app feedback widget + interviews | Developer | $0 | P0 | Beta users
W3 | Content marketing: 3 blog posts (SEO-optimized) | Writer | $600 | P1 | SEO audit
W3 | Product Hunt: prep listing, screenshots, GIF demos | Marketing | $200 | P1 | Beta feedback
W4 | Bug fixing sprint based on beta feedback | Developer | $0 | P0 | Beta feedback
W4 | App Store Optimization (if PWA) | Marketing | $300 | P2 | None
W4 | Referral system: invite friends for premium credits | Developer | $300 | P1 | Stripe ready
W4 | Testimonials: collect from beta users | Founder | $0 | P1 | Beta users
PHASE 3: PUBLIC LAUNCH (Weeks 5-8)
W5 | Product Hunt launch day | Founder+Team | $0 | P0 | PH listing ready
W5 | Press outreach: EdTech blogs, TechCrunch, etc. | PR Agency | $1,200 | P1 | Press kit
W5 | Google Ads campaign: EdTech keywords | Marketing | $1,000/mo | P1 | Landing page
W5 | Social media ads: Instagram, TikTok (student demo) | Marketing | $500/mo | P1 | Creative assets
W6 | YouTube tutorial: 'How NoteSnap works' (2-3 min) | Video prod. | $800 | P1 | None
W6 | University/school outreach: pilot programs | BD | $0 | P2 | Product stable
W7 | Influencer partnerships: EdTech YouTubers/TikTokers | Marketing | $1,000-3,000 | P1 | Budget approval
W7 | Community: Discord/Telegram group for users | Community mgr | $200 | P2 | 100+ users
W8 | Iteration sprint: top feedback → feature updates | Developer | $0 | P0 | User data
W8 | A/B test pricing page for conversion optimization | Developer | $0 | P1 | Traffic data
PHASE 4: GROWTH (Months 3-12)
M3 | Retention optimization: reduce churn with engagement hooks | Developer | $0 | P0 | Churn data
M3 | Localization: expand to 3-5 more languages | Translators | $2,000 | P1 | i18n framework
M4 | API/SDK: allow schools to integrate NoteSnap | Developer | $0 | P2 | Product stable
M4 | Teacher dashboard: class management features | Developer | $0 | P1 | School pilots
M6 | Mobile app (React Native or native) | Developer | $5,000-15,000 | P2 | Web stable
M6 | Enterprise plan: school/university licensing | BD+Legal | $2,000 | P1 | Teacher dashboard
M9 | Series A prep: metrics deck, financial model | Founder+CFO | $3,000 | P1 | Traction
M12 | Review: annual metrics, pivot/scale decisions | Team | $0 | P0 | 12-mo data

## Risk Analysis
Risk Analysis & Mitigation
Risk | Probability | Impact | Mitigation
AI API costs exceed projections | Medium | High | Implement usage caps per user tier; cache common responses; use Haiku for simple tasks
Low user conversion to paid | High | High | A/B test pricing; offer annual discount; strong onboarding; free tier with clear upgrade path
Claude API rate limits / outages | Low | Critical | Implement request queuing; graceful degradation; fallback to cached content
Competitor launches similar product | Medium | Medium | Focus on niche (Hebrew+English); build community moat; iterate faster
GDPR / data privacy issues | Low | Critical | Hire legal counsel; data residency in EU; privacy-by-design architecture
Technical debt slows development | Medium | Medium | Allocate 20% sprint time to refactoring; maintain test coverage >80%
Single founder burnout | High | Critical | Hire key contractor early; automate operations; set sustainable pace
Supabase free tier limits hit | Medium | Low | Monitor usage; upgrade plan proactively; optimize queries
Student data sensitivity concerns | Medium | High | No PII collection; anonymized analytics; parental consent flow
Exchange rate risk (USD costs, local revenue) | Medium | Medium | Price in USD globally; hedge with multi-currency Stripe